## Sheet1
Item | Description | PRRIP FY23 Budget Line Item | PRRIP FY23 Budget Amount | PRRIP FY23 Contracted Amount | EDO Staff Lead | Contracted Entity | Competitive Selection Process? | Procurement Threshold | Process | EDO Timeline | Advisory Committee Review for 2023 | FC Review/Approval for 2023 | GC Review/Approval for 2023
PRRIP Administration
PRRIP Website & Database | Contractor services to maintain the PRRIP website, monitoring databases, and financial management database | PD-8 | 77000 | 0 | Justin Brei | DJ Case | Y | > $50,000 | DJ Case hired through competitive selection process, currently under contract through 2023 | Contract amendment drafted, internal technical/process review complete | n/a | n/a | December 2022 - approve one-year contract amendment for 2023
Subtotal |  |  | 77000 | 0
Land Plan
Prescribed Fire | Contractor services for prescribed fire on PRRIP properties | LP-2 | 82459 | 0 | Tim Tunnell | TBD | Y | > $50,000 | Competive selection process (RFP) for multi-year contract | RFP and contract form drafted, internal technical/process review complete | n/a | n/a | December 2022 - approve RFP, approve contract form, appoint Proposal Selection Panel (if necessary)
Chemical Application Services | Contractor services for herbicide spraying on PRRIP properties to control noxious weeds | LP-2, LP-4, WPLW | 214500 | 0 | Tim Tunnell | TBD | Y | > $50,000 | Competitive selection process (RFB) for multi-year contract | RFB and contract form drafted, internal technical/process review complete | n/a | n/a | December 2022 - approve RFB, approve contract form
Complex Activities (Pawnee, Fort Kearny, Clark Island) | In-channel disking | LP-2 | 85500 | 0 | Tim Tunnell | TBD | Y | > $50,000 | Competitive selection process (RFQ) for one-year contract | RFQ drafted; internal technical/process review by June | n/a | Late July/early August - approve RFQ and contract form (one-year contract) | n/a
Subtotal |  |  | 382459 | 0
\
Elwood Recpature | Contractor services RFP for expanded recpature and associated groundwater modeling | WPRT-4 | 200000 | 0 | Seth Turner | TBD | Y | > $50,000 | Competitive selection process (RFP) for one-year project | Draft RFP and contract form by April; internal technical/process review by end of April | May -- WAC review of scope | May -- review RFP and approve for posting (if GC approves scope in June); approve contract form | June -- approve scope of RFP; appoint Proposal Selection Panel
North Platte chokepoint | Qualfications-based RFP for contractor services to scope and implement further study of options at chokepoint (post-PRRIP land acquisition and post-VESPR study) | WPCP-1 | 400000 | 0 | Seth Turner | TBD | Y | > $50,000 | Competitive selection process (RFP) for one-year project | Draft RFP and contract form by April; internal technical/process review by end of April | May -- WAC review of scope | May -- review RFP and approve for posting (if GC approves scope in June); approve contract form | June -- approve scope of RFP; appoint Proposal Selection Panel
Subtotal |  |  | 600000 | 0
Science Plan
Predator Trapping | Trapping at PRRIP OCSW sites to reduce predation impacts on tern/plover productivity | LP-2-P | 97600 | 0 | Malinda Henry | USDA/APHIS | Sole-source | > $50,000 | Sole-source justification (unique qualifications; lack of experienced/permitted options) | Sole-source memo, Cooperative Service Agreement, and 2023 scope/budget drafted; internal technical/process review complete | n/a | n/a | December 2022 - approve sole-source acquisition, approve Cooperative Service Agreement (multi-year contract)
Sediment Augmentation | Full-scale sediment augmentation (80,000 tons) | PD-22 | 260000 |  | Ed Weschler | TBD | Y | > $50,000 | RFB for implementation in 2023 (one year contract) | TBD | TBD | TBD | TBD
WC Monitoring | Contractor assistance with implementing PRRIP WC monitoring protocol (pilots, aircraft, crews) | WC-1 | 58000 | 0 | Mallory Jaymes | TBD | Y | > $50,000 | RFB for two migration seasons (spring/fall) in one calendar year | RFB and contract form drafted, internal technical/process review complete | n/a | n/a | December 2022 - approve RFB and contract form
Lower Platte River (LPR) 2D Hydrodynamic Modeling | 2D hydrodynamic modeling from LPR LiDAR flown in 2022 | PS-1 | 250000 | 0 | Libby Casavant | TBD | Y | > $50,000 | RFP for one-time model development, one-year contract | Draft RFP and contract form by March; internal technical/process review by end of March | April -- TAC review of RFP | May -- approve RFP and contract form (one-year contract) | n/a
Remote Sensing | Annual acqusition of LiDAR | G-1 | 305200 | 0 | Helen Davis | TBD | Y | > $50,000 | RFP for multi-year contract (4 years) | Draft RFP and contract form by September; internal technical/process review by end of September | October -- TAC review of RFP | November -- review RFP and contract form | December -- approve RFP and contract form
ISAC | Appoint new ISAC member in 2023, approve 3-year contract for new ISAC member, approve annual contract amendments for other five (5) ISAC members | ISAC-1 | 232800 | 0 | Chad Smith | New ISAC member to replac Ned Andrews TBD; retain other existing five (5) ISAC members | Retention exception, modified selection process | n/a | New ISAC selection materials, management of selection process with ISAC Selection Panel | New ISAC member selection materials drafted by January; internal technical/process review by end of January; contract form for new ISAC member and contract amendments for existing ISAC members drafted by April; internal technical/process review by end of April | February - TAC review of new ISAC member selection materials | May -- review contract form for new ISAC member; approve annual contract amendments for existing five (5) ISAC members | June -- appoint new ISAC member, approve three-year contract
Peer Review | Appoint peer review panel for two (2) PRRIP documents. | PD-3 | 54000 | 0 | Chad Smith | TBD | Retention exception, modified selection process | n/a | Peer Review Panel member selection materials, management of selection process with Peer Reviewer Selection Panel | Peer review documents and peer review panel selection materials drafted by March; internal technical/process review by end of March; peer review panel member contract forms drafted by July, internal technical/process review by end of July | April -- TAC review of peer review documents | August -- approve contract forms for peer review panel members | March -- appoint Peer Reviewer Selection Panel; June -- approve Peer Review Panel member selection materials; September - appoint Peer Review Panel members
Subtotal |  |  | 1257600 | 0