## 2019 PRRIP Budget
NOTE: The total PRRIP budget through 2032 may exceed authorized expenditures until Water Action Plan (WAP) projects are selected for implementation.
PRRIP Project ID | Status | PRRIP Project Description | FY 2007 Final Budget | FY 2007 Expenditures | FY 2008 Budget (New Money + FY 2007 UO) | FY 2008 Expenditures | FY 2009 Budget (New Money + FY 2008 UO) | FY 2009 Expenditures | FY 2010 Budget (New Money + FY 2009 UO) | FY 2010 Expenditures | FY 2011 Budget (New Money) | FY 2011 Expenditures | FY 2012 Budget (New Money) | FY 2012 Expenditures | FY2013 Budget (New Money) | FY 2013 Expenditures | FY 2014 Approved Budget | FY 2014 Expenditures | FY 2015 Expenditures | FY 2016 Expenditures | FY 2017 Expenditures | FY 2018 Expenditures (as of 11/30/18) | FY 2019 Estimated New Money | "Quick Reference" Comments on FY 2019 New Money Budget Estimates (see FY 2019 Work Plan for Full Description) | FY 2020 Estimated New Money | FY 2021 Estimated New Money | FY 2022 Estimated New Money | FY 2023 Estimated New Money | FY 2024 Estimated New Money | FY 2025 Estimated New Money | FY 2026 Estimated New Money | FY 2027 Estimated New Money | FY 2028 Estimated New Money | FY 2029 Estimated New Money | FY 2030 Estimated New Money | FY 2031 Estimated New Money | FY 2032 Estimated New Money
|  |  | Column A | Column A | Column C | Column B | Column E | Column C | Column G | Column D | Column I | Column E | Column F | Coulumn F | Column H | Column G | Column H | Column H | Column I | Column J | Column K | Column L | Column M | Column N | Column O | Column P | Column Q | Column R | Column S | Column T | Column U | Column V | Column W | Column X | Column Y | Column Z | Column AA
Executive Director's Office (ED)
ED-1 | O | Salaries/Travel/Office Expenditures (FY08-FY19) | 192688 | 210292.78 | 1110600 | 1220138.33 | 1427759 | 1535891.24 | 1599900 | 1650847.94 | 1600000 | 1725903.82 | 1800000 | 1845945.69 | 1875000 | 1903370.23 | 2200000 | 1991367.46 | 2126847.97 | 2361081.69 | 2355814.09 | 2037041.98 | 2400000 | Salaries, travel, and other direct costs associated with ED and staff in ED Office. | 2400000 | 2400000 | 2400000 | 2400000 | 2400000 | 2400000 | 2400000 | 2400000 | 2400000 | 2400000 | 2400000 | 2400000 | 2400000
ED-2 | O | Administrative and Other Support Services (FY08-FY19) | 411861 | 348673.3 | 170614.52 | 87493.91 | 250000 | 156323.84 | 200000 | 88096.51 | 200000 | 152262.3 | 150000 | 172961.05 | 150000 | 63318.9 | 100000 | 67563.24 | 113995.51 | 85917.51 | 101799.67 | 129305.03 | 142000 | Public notices, land and water specialty attorneys, and other miscellaneous services required to support ED efforts. | 142000 | 120000 | 120000 | 120000 | 120000 | 120000 | 120000 | 120000 | 120000 | 120000 | 120000 | 120000 | 120000
ED-3 | O | Public Outreach (FY09-FY19) | 0 | 0 | 0 | 0 | 30000 | 30310.63 | 40000 | 32606.7 | 50000 | 50381.58 | 70000 | 70335.38 | 65000 | 64973.54 | 60000 | 59783.32 | 74321.02 | 68802.52 | 57050.3 | 49281.29 | 60000 | Exhibit fees, major sponsorships, other sponsorships, promotional materials including Biennial Report. | 60000 | 60000 | 60000 | 60000 | 60000 | 60000 | 60000 | 60000 | 60000 | 60000 | 60000 | 60000 | 60000
|  | Sub-Total | 604549 | 558966.08 | 1281214.52 | 1307632.24 | 1707759 | 1722525.71 | 1839900 | 1771551.15 | 1850000 | 1928547.7 | 2020000 | 2089242.12 | 2090000 | 2031662.67 | 2360000 | 2118714.02 | 2315164.5 | 2515801.72 | 2514664.06 | 2215628.3 | 2602000 | 25692100.27 | 2602000 | 2580000 | 2580000 | 2580000 | 2580000 | 2580000 | 2580000 | 2580000 | 2580000 | 2580000 | 2580000 | 2580000 | 2580000 | 33562000
Governance Committee/Finance Committee (GFC)
GFC-1 | O | NCF Fees (FY08-FY19) | 75000 | 22147.61 | 100000 | 77178.48 | 255000 | 235881.2 | 260000 | 206470.89 | 300000 | 195565.15 | 450000 | 327323.13 | 450000 | 414896.52 | 250000 | 121023.1 | 240373.46 | 458766.26 | 297738.88 | 251519.81 | 450000 | Annual fees for Financial Management Entity services. | 450000 | 450000 | 450000 | 450000 | 300000 | 300000 | 300000 | 300000 | 300000 | 300000 | 300000 | 300000 | 300000
GFC-2 | O | Flow Releases and Other Insurance (FY08-FY19) | 100000 | 2448.21 | 50000 | 41834 | 60000 | 56394 | 70000 | 62632 | 75000 | 69026 | 70000 | 64870.55 | 75000 | 74531 | 75000 | 77212 | 75228 | 78983 | 69675.8 | 77738.98 | 85000 | Program insurance for flow releases and liability; insurance for vehicles and liability for airboat now on Headwaters. | 85000 | 85000 | 85000 | 85000 | 85000 | 85000 | 85000 | 85000 | 85000 | 85000 | 85000 | 85000 | 85000
GFC-3 | O | Expenses, Meeting Rooms, etc. (FY08-FY19) | 5000 | 1001.82 | 5000 | 1500.12 | 5000 | 3378.95 | 5000 | 499.92 | 1000 | 2720.26 | 1500 | 9269.33 | 1500 | 3126.35 | 1700 | 7535.39 | 7542.78 | 9119.98 | 4561.75 | 3333.37 | 4400 | Expenses associated with GC meetings outside of Kearney. | 4000 | 4000 | 4000 | 4000 | 4000 | 4000 | 4000 | 4000 | 4000 | 4000 | 4000 | 4000 | 4000
GFC-4 | O | SDHF Reserve (FY09-FY19) | 0 | 0 | 0 | 0 | 1000000 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | Annual reserve for potential EA bypass-related costs. | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0
|  | Sub-Total | 180000 | 25597.64 | 155000 | 120512.6 | 1320000 | 295654.15 | 335000 | 269602.81 | 376000 | 267311.41 | 521500 | 401463.01 | 526500 | 492553.87 | 326700 | 205770.49 | 323144.24 | 546869.24 | 371976.43 | 332592.16 | 539400 | 4192448.05 | 539000 | 539000 | 539000 | 539000 | 389000 | 389000 | 389000 | 389000 | 389000 | 389000 | 389000 | 389000 | 389000 | 5657000
Program Advisory Committees
LAC-1 | O | Expenses, Meeting Rooms, etc. (FY08-FY19) | 7500 | 201.36 | 7500 | 414.04 | 7500 | 245.56 | 7500 | 0 | 1000 | 785.4 | 1500 | 1283.14 | 2000 | 921.36 | 1600 | 757.46 | 877.14 | 391.38 | 725.66 | 258.4 | 700 | Conference line and other associated costs for LAC meetings. | 700 | 700 | 700 | 700 | 700 | 700 | 700 | 700 | 700 | 700 | 700 | 700 | 700
WAC-1 | O | Expenses, Meeting Rooms, etc. (FY08-FY19) | 5000 | 0 | 5000 | 23.56 | 5000 | 0 | 5000 | 0 | 1000 | 2330.9 | 1500 | 5457.54 | 6000 | 1731.62 | 3500 | 1107.48 | 1597.3 | 1660.12 | 1015.08 | 2292.38 | 2500 | Conference line and other associated costs for WAC meetings. | 2500 | 2500 | 2500 | 2500 | 2500 | 2500 | 2500 | 2500 | 2500 | 2500 | 2500 | 2500 | 2500
TAC-1 | O | Expenses, Meeting Rooms, etc. (FY08-FY19) | 5000 | 820 | 5000 | 75 | 5000 | 864.3 | 5000 | 0 | 1000 | 1231.56 | 1500 | 2246.87 | 4000 | 2436.72 | 2400 | 1117.44 | 1012.44 | 904.2 | 1261.98 | 582.44 | 2000 | Conference line and other associated costs for TAC meetings. | 2000 | 2000 | 2000 | 2000 | 2000 | 2000 | 2000 | 2000 | 2000 | 2000 | 2000 | 2000 | 2000
|  | Sub-Total | 17500 | 1021.36 | 17500 | 512.6 | 17500 | 1109.86 | 17500 | 0 | 3000 | 4347.86 | 4500 | 8987.55 | 12000 | 5089.7 | 7500 | 2982.38 | 3486.88 | 2955.7 | 3002.72 | 3133.22 | 5200 | 41829.83 | 5200 | 5200 | 5200 | 5200 | 5200 | 5200 | 5200 | 5200 | 5200 | 5200 | 5200 | 5200 | 5200 | 67600 | 39328429.83
Land Plan Implementation (LP)
- | C | Land Interest Holding Entity Negotiations & Start-Up (FY07) | 10000 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | Complete from PRRIP budget standpoint. | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0
LP-3 | O | Land Acquisition (FY09-FY19) | 0 | 0 | 6000000 | 57235.61 | 7000000 | 8875890.01 | 6000000 | 3335269.11 | 5000000 | 2108612.42 | 5000000 | 6395100.41 | 3000000 | 892217.18 | 1500000 | 1615655.97 | 369765.76 | 260613.13 | 2862306.47 | 265581.24 | 2600000 | Land acquisition costs for 2019; annual LIHE fees and property taxes. | 2600000 | 2600000 | 260000 | 260000 | 260000 | 260000 | 260000 | 260000 | 260000 | 260000 | 260000 | 260000 | 260000
LP-4 | O | Land Management (FY09-FY19) | 0 | 0 | 0 | 0 | 500000 | 116216.05 | 588800 | 587818.14 | 365500 | 366316.52 | 409800 | 314190.47 | 448400 | 288351.53 | 192500 | 239294.96 | 264309.05 | 277527.05 | 167747.1 | 126685.18 | 195200 | Basic land operations and maintenance including road, fence, and building upkeep, noxious weed control, mowing, etc. Agricultural input costs for share cropping agreements including seed, fertilizer and herbicide application, crop insurance, etc. | 250000 | 250000 | 250000 | 250000 | 250000 | 250000 | 250000 | 250000 | 250000 | 250000 | 250000 | 250000 | 250000
LP-5 | C | Cottonwood Ranch Bridge Final Design & Construction (FY10-FY16) | 0 | 0 | 0 | 0 | 0 | 25576.24 | 250000 | 48087.64 | 250000 | 171130.79 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | Complete from PRRIP budget standpoint. | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0
LP-6 | O | Land Plan Special Advisors (FY10-FY19) | 0 | 0 | 0 | 0 | 0 | 0 | 50000 | 59115.02 | 150000 | 48726.16 | 120000 | 15717.64 | 50000 | 19105.45 | 20000 | 19704.7 | 15166.4 | 15974.95 | 13098.5 | 0 | 20000 | Land-related specialty items such as land leases, Farm Service Agency (FSA) reporting, and rent collections on all complex and non-complex properties. Advisors shall continue annually on all land to the end of the First Increment. | 20000 | 20000 | 20000 | 20000 | 20000 | 20000 | 20000 | 20000 | 20000 | 20000 | 20000 | 20000 | 20000
LP-7 | O | Public Access Management (FY11-FY19) | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 50000 | 50000 | 50000 | 50000 | 55000 | 50065 | 50000 | 51388.5 | 50000 | 53436.91 | 50000 | 0 | 50000 | Nebraska Game and Parks Commission is the contracted provider. | 50000 | 50000 | 50000 | 50000 | 50000 | 50000 | 50000 | 50000 | 50000 | 50000 | 50000 | 50000 | 50000
|  | Sub-Total | 10000 | 0 | 6000000 | 57235.61 | 7500000 | 9017682.3 | 6888800 | 4030289.91 | 5815500 | 2744785.89 | 5579800 | 6775008.52 | 3553400 | 1249739.16 | 1762500 | 1926044.13 | 699241.21 | 607552.04 | 3093152.07 | 392266.42 | 2865200 | 33458197.26 | 2920000 | 2920000 | 580000 | 580000 | 580000 | 580000 | 580000 | 580000 | 580000 | 580000 | 580000 | 580000 | 580000 | 12220000
Water Plan Implementation (WP)
WP-1(a) | O | Active Channel Capacity Improvements (N. Platte Channel above CNPPID Diversion Dam) (FY07-FY17) | 241000 | 110690.94 | 153210 | 10805.5 | 161529.5 | 149886.6 | 61642.9 | 36104.18 | 250000 | 36789.63 | 100000 | 28297.28 | 500000 | 180167.27 | 260000 | 30856.11 | 29761.3 | 231084.36 | 175368.19 | 80890 | 10500 | Efforts to increase North Platte River channel capacity including $5,500 for monitoring of a planned high flow releases and $5,000 for maintenance of the State Channel berm. | 5000 | 5000 | 5000 | 5000 | 5000 | 5000 | 5000 | 5000 | 5000 | 5000 | 5000 | 5000 | 5000
WP-1(b) | O | Active Channel Capacity Improvements (CNPPID Diversion Dam to Grand Island) (FY10-FY19) | 0 | 0 | 0 | 0 | 0 | 0 | 400000 | 400000 | 200000 | 200000 | 200000 | 200000 | 200000 | 200000 | 100000 | 100000 | 200000 | 300000 | 300000 | 300000 | 200000 | In-channel maintenance efforts to control Phragmites; joint project effort with the NRDs, Program, and other participants. | 200000 | 200000 | 200000 | 200000 | 200000 | 200000 | 200000 | 200000 | 200000 | 200000 | 200000 | 200000 | 200000
WP-2(a) | C | Water Management Study Phase 1 (FY07-FY08) | 124000 | 119016.12 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | Complete from PRRIP budget standpoint. | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0
WP-2(b) | C | Water Management Study Phase II (FY08) | 0 | 0 | 157000 | 155969.84 | 0 | 0 | 0 | 0 | 0 |  | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | Complete from PRRIP budget standpoint. | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0
WP-3 | C | Test Flow Routing Model/2008 EA Augmented SDHF Pilot Study (FY09) | 75000 | 23471 | 0 | 0 | 0 | 65678.08 | 0 | 0 | 0 |  | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | Complete from PRRIP budget standpoint. | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0
WP-4(a) | C | Water Action Plan (J2 Rereg Reservoir) (FY09-FY19) | 0 | 0 | 0 | 0 | 250000 | 29272.57 | 0 | 0 | 5100000 | 0 | 9000000 | 223820.22 | 13000000 | 14612380.23 | 14392000 | 0 | 0 | 0 | 1964.56 | 1964.56 | 0 | Project on hold, no anticipated expenditures in 2019. | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0
WP-4(b)i | O | Water Action Plan (CNPPID system groundwater projects) (FY12-FY19) |  | 0 |  | 0 |  | 0 |  | 0 |  | 0 |  | 6790.86 |  | 151050 | 88296 | 53263.53 | 758109.02 | 462901.96 | 647529.36 | 218271.56 | 735000 | Includes $128,000 for Phelps County Canal groundwater recharge project, $582,000 for Elwood Reservoir recharge, and $25,000 for related groundwater recharge recapture projects. | 4800000 | 800000 | 800000 | 800000 | 800000 | 800000 | 800000 | 800000 | 800000 | 800000 | 800000 | 800000 | 800000
WP-4(b)ii | O | Water Action Plan (broad-scale recharge) (FY16-FY19) |  | 0 |  | 0 |  | 0 |  | 0 |  | 0 |  | 0 |  | 0 |  | 0 | 0 | 121497 | 308076.59 | 1182001.84 | 2428875 | Includes $75,000 for construction oversight, $15,000 for groundwater monitoring equipment and $2,340,875 for land acquisition associated with a recapture network. | 2500000 | 400000 | 400000 | 400000 | 400000 | 400000 | 400000 | 400000 | 400000 | 400000 | 400000 | 400000 | 400000
WP-4(b)iii | C | Water Action Plan (other recharge) (FY17-FY19) |  | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | Not anticipated at this time. | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0
WP-4(c)i | C | Water Action Plan (No Cost NCCW) (FY17-FY19) | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 1500000 | 0 | 26250 | 0 | 0 | 0 | 0 | 0 | 0 | Complete from PRRIP budget standpoint. | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0
WP-4(c)ii | C | Water Action Plan (Purchased No Cost NCCW) (FY17-FY19) | [12 empty] | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | Not anticipated at this time. | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0
WP-4(d) | O | Water Action Plan (Pathfinder Municipal Accnt) (FY12) | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 2000000 | 1958400 | 0 | 0 | 0 | 0 | 0 | 0 | 312000 | 526500 | 624000 | Budget allows for purchase of maximum lease volume 9,600 AF at a cost of $65 per AF. | 503000 | 503000 | 503000 | 503000 | 503000 | 503000 | 503000 | 503000 | 503000 | 503000 | 503000 | 503000 | 503000
WP-4(e) | C | Water Action Plan (CO GW Mgmnt) (FY17-FY19) | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 1854667 | 0 | 0 | 0 | 0 | 0 | 0 | Not anticipated at this time. | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0
WP-4(f)i | O | Water Action Plan (CPNRD leasing) (FY13-FY19) | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 500000 | 0 | 150000 | 34156.5 | 0 | 0 | 685013.16 | 747205.83 | 2203138 | 662.5 | 2397000 | Includes $2,260,000 for 14,200 AF surface water transfer and $137,000 for 3,000 AF of groundwater recharge accretions. | 2400000 | 2400000 | 2400000 | 2400000 | 2400000 | 2400000 | 2400000 | 2400000 | 2400000 | 2400000 | 2400000 | 2400000 | 2400000
WP-4(f)ii | O | Water Action Plan (NPPD leasing) (FY16-FY19) |  | 0 |  | 0 |  | 0 |  | 0 |  | 0 |  | 0 | 0 | 0 | 0 | 0 | 133623 | 260043 | 107820 | 0 | 277400 | Includes $117,400 for 718 AF surface water transfer and $160,000 for 5,000 AF of groundwater recharge diversions. | 277000 | 277000 | 277000 | 277000 | 277000 | 277000 | 277000 | 277000 | 277000 | 277000 | 277000 | 277000 | 277000
WP-4(f)iii | O | Water Action Plan (CNPPID leasing -storage) (FY17-FY19) |  | 0 |  | 0 |  | 0 |  | 0 |  | 0 |  | 0 | 0 | 0 | 148750 | 0 | 0 | 0 | 0 | 0 | 0 | Not anticipated at this time. | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0
WP-4(f)iv | O | Water Action Plan (CNPPID leasing-irrigator) (FY16-FY19) |  | 0 |  | 0 |  | 0 |  | 0 |  | 0 |  | 0 |  | 0 | 198360 | 0 | 0 | 238140 | 290500 | 462100 | 670000 | Includes 3,000 acres enrolled at $220 per acre and $10,000 administsrative fee. | 670000 | 670000 | 670000 | 670000 | 670000 | 670000 | 670000 | 670000 | 670000 | 670000 | 670000 | 670000 | 670000
WP-4(f)v | O | Water Action Plan (NPNRD leasing) (n/a) |  | 0 |  | 0 |  | 0 |  | 0 |  | 0 |  | 0 |  | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 150000 | 2019 budget includes funding to support ongoing NPNRD water retirement programs such as allocation buy-down. | 150000 | 150000 | 150000 | 150000 | 150000 | 150000 | 150000 | 150000 | 150000 | 150000 | 150000 | 150000 | 150000
WP-4(f)vi | O | CPNRD Groundwater Market (FY16-FY-19) |  | 0 |  | 0 |  | 0 |  | 0 |  | 0 |  | 0 |  | 0 |  | 0 | 0 | 8748.71 | 0 | 0 | 0 | Not anticipated at this time. | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0
WP-4(f)vii | O | Water Action Plan (Acquire & Retire) (FY17-FY19) |  | 0 |  | 0 |  | 0 |  | 0 |  | 0 |  | 0 |  | 0 |  | 0 | 0 | 0 | 18193.09 | 1500 | 0 | Not anticipated at this time. | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0
WP-4(f)viii | N | Water Action Plan (North Platte canals leasing) (FY19-FY32) |  | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 750000 | Includes leasing of up to 5,000 AF of water to be stored in EA. | 750000 | 750000 | 750000 | 750000 | 750000 | 750000 | 750000 | 750000 | 750000 | 750000 | 750000 | 750000 | 750000
WP-4(g) | C | Water Action Plan (Water Mgmnt Incentives) (FY17-FY19) | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 5000 | 24500 | 25000 | Program supporting efforts to improve management of irrigation resources. | 25000 | 25000 | 25000 | 25000 | 25000 | 25000 | 25000 | 25000 | 25000 | 25000 | 25000 | 25000 | 25000
WP-4(h) | C | Water Action Plan (NE GW Mgmnt) (FY13-FY19) | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 100000 | 0 | 250000 | 47091.78 |  | 0 | 0 | 0 | 0 | 0 | 0 | No projects anticipated at this time. | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0
WP-4(i) | O | Water Action Plan (Slurry Wall Gravel Pits) (FY17-FY19) |  | 0 |  | 0 |  | 0 |  | 0 |  | 0 |  | 0 |  | 0 |  | 0 | 0 | 0 | 852640.69 | 264231.31 | 9606000 | Includes $9,246,000 for slurry wall construction and $360,000 for wetland mitigation associated with slurry wall project and new mine site. | 200000 | 200000 | 200000 | 200000 | 200000 | 200000 | 200000 | 200000 | 200000 | 200000 | 200000 | 200000 | 200000
WP-4(j) | O | General maintenance of land-for-water properties (FY18-FY19) | 0 | 0 | 0 | 0 | 0 | 0 | 100000 | 0 | 200000 | 0 | 50000 | 0 | 50000 | 0 | 90000 | 0 | 0 | 0 | 0 | 35915.92 | 70300 | Includes irrigation management, fence and road maintenance, noxious weed spraying and other tasks at Program properties planned for future water projects. Includes taxes for land associated with water. | 108300 | 108300 | 108300 | 108300 | 108300 | 108300 | 108300 | 108300 | 108300 | 108300 | 108300 | 108300 | 108300
WP-5 | C | Management Tool (FY12-FY17) | 0 | 0 | 0 | 0 | 0 | 0 | 100000 | 0 | 200000 | 0 | 50000 | 0 | 50000 | 3520.71 | 90000 | 33658.41 | 177800.59 | 58540 | 16000 | 0 | 14400 | COHYST technical oversight and training. | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0
WP-6 | C | Feasibility Studies (FY09-FY12) | 0 | 0 | 0 | 0 | 500000 | 392539.35 | 2050000 | 486884.73 | 600000 | 625483.22 | 0 | 133455.96 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | Not anticipated at this time. | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0
WP-7 | C | Water Acquisition (FY09-FY11) | 0 | 0 | 0 | 0 | 500000 | 0 | 500000 | 0 | 300000 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 1723909.52 | 0 | 3500 | 0 | Complete from PRRIP budget standpoint. | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0
WP-8 | O | Water Plan Special Advisors (FY10-FY19) | 0 | 0 | 0 | 0 | 0 | 0 | 150000 | 92651.89 | 200000 | 141029.41 | 150000 | 143385.55 | 125000 | 58984.48 | 100000 | 77852.14 | 191947.11 | 261013.1 | 106312.48 | 107686.76 | 156000 | Advisors on water-related specialty topics such as hydro-geology/ground water, structural engineering and streamflow forecasting. | 150000 | 150000 | 150000 | 150000 | 15000 | 150000 | 50000 | 50000 | 50000 | 50000 | 50000 | 50000 | 50000
WP-9 | C | Miscellaneous Water Resources Studies (FY10-FY16) | 0 | 0 | 0 | 0 | 0 | 0 | 200000 | 30109.77 | 100000 | 17147.85 | 50000 | 36107.66 | 25000 | 0 | 0 | 6566.18 | 26977.62 | 26239.63 | 0 | 0 | 0 | Not anticipated at this time. | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0
- | C | Legal Review for North Platte Channel Capacity Project (FY08) | 10000 | 0 | 5000 | 2975 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | Complete from PRRIP budget standpoint. | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0
|  | Sub-Total | 450000 | 253178.06 | 315210 | 169750.34 | 1411529.5 | 637376.6 | 3561642.9 | 1045750.57 | 7150000 | 1020450.11 | 12200000 | 2730257.53 | 15850000 | 15287350.97 | 17348323 | 302196.37 | 2203231.8 | 4439323.11 | 5344542.96 | 3209724.45 | 18114475 | 54757607.87 | 12738300 | 6638300 | 6638300 | 6638300 | 6503300 | 6638300 | 6538300 | 6538300 | 6538300 | 6538300 | 6538300 | 6538300 | 6538300 | 91562900
AMP Experimental Design
PD-4 | O | AMP Workshops (FY09-FY21) | 50000 | 9599.55 | 75000 | 49025.72 | 10000 | 274.09 | 10000 | 0 | 10000 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 20000 | Meeting costs for AMP update process. | 20000 | 20000 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 20000 | 20000 | 20000 | 20000
PD-12 | C | Model Application (FY09-FY13) | 0 | 0 | 0 | 0 | 360000 | 0 | 390000 | 348094.61 | 150000 | 177467.55 | 20000 | 0 | 10000 | 1997.1 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | Complete from PRRIP budget standpoint. | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0
PD-13 | C | Sediment Augmentation Feasibility Analysis, Design, and Permitting (FY09-FY13) | 0 | 0 | 0 | 0 | 400000 | 89208.79 | 520791.21 | 320791.21 | 350000 | 145831.72 | 540888 | 505117.78 | 671404 | 681104.94 | 0 | 237060.3 | 0 | 0 | 0 | 0 | 0 | Complete from PRRIP budget standpoint. | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0
PD-14 | C | Whooping Crane Conservation Action Plan (CAP) Development (FY09) | 0 | 0 | 0 | 0 | 20000 | 20000 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | Complete from PRRIP budget standpoint. | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0
PD-19 | C | Flow Consolidation Conceptual Design (FY10-FY13) | 0 | 0 | 0 |  | 0 | 0 | 200000 | 81677.06 | 200000 | 104277.64 | 230000 | 59500.76 | 100000 | 43042.6 | 0 | 37720 | 0 | 0 | 0 | 0 | 0 | Complete from PRRIP budget standpoint. | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0
PD-20 | C | Wet Meadow Restoration on Tract 2009001 (FY11-FY13) | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 50000 | 31375.94 | 324000 | 203614.19 | 45000 | 120867.56 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | Complete from PRRIP budget standpoint. | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0
- | C | Develop Mgmt.-Level Hypothesis Testing for FSM/Clear-Level Plow (FY07) | 25000 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | Complete from PRRIP budget standpoint. | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0
|  | Sub-Total | 75000 | 9599.55 | 75000 | 49025.72 | 790000 | 109482.88 | 1120791.21 | 750562.88 | 760000 | 458952.85 | 1114888 | 768232.73 | 826404 | 847012.2 | 0 | 274780.3 | 0 | 0 | 0 | 0 | 20000 |  | 20000 | 20000 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 20000 | 20000 | 20000 | 20000 | 120000
AMP Implementation Activities
- | C | AMWG Assistance & Operating Expenses | 0 | 13620.15 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | Complete from PRRIP budget standpoint. | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0
LP-2 | O | FSM/MCM Actions at Habitat Complexes (FY08-FY19) | 25000 | 3675 | 0 | 0 | 350000 | 187879.35 | 1270000 | 493536.21 | 483000 | 650585.59 | 639130 | 744190.85 | 890450 | 339691.9 | 432080 | 260341.18 | 546036.47 | 351037.64 | 294980 | 218057.71 | 2168452 | General actions at habitat complexes; see FY19 Annual Land Work Plan for specific details. | 400000 | 400000 | 400000 | 400000 | 400000 | 400000 | 400000 | 400000 | 400000 | 400000 | 400000 | 400000 | 400000
LP-2(a) | C | Cottonwood Ranch Maintenance & Enhancement (FY07-FY08) | 75000 | 0 | 550000 | 251710.1 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | Complete from PRRIP budget standpoint. | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0
LP-2(b) | C | Pre-2007 Cottonwood Ranch Maintenance & Enhancement (FY08) | 0 | 0 | 850000 | 848836.22 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | Complete from PRRIP budget standpoint. | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0
WP-10 | O | Environmental Account SDHF (FY08-FY19) | 0 | 0 | 250000 | 46872.33 | 350000 | 2198.47 | 0 | 0 | 150000 | 0 | 0 | 0 | 150000 | 42940 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | No SDHF planned in 2019. | 0 | 0 | 0 | 150000 | 0 | 0 | 150000 | 0 | 0 | 0 | 0 | 0 | 0
PD-7 | C | Program Anchor Points (FY09) | 50000 | 0 | 50000 | 0 | 50000 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | Complete from PRRIP budget standpoint. | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0
PD-15 | O | Environmental Permitting (FY09-FY19) | 0 | 0 | 0 | 0 | 10000 | 0 | 50000 | 50000 | 200000 | 127993.21 | 150000 | 30162.13 | 50000 | 31287.93 | 50000 | 0 | 3428.52 | 47061.4 | 46848.4 | 45699.67 | 50000 | Assistance with permitting for channel widening and full-scale sediment augmentation (mechanical). | 50000 | 50000 | 50000 | 50000 | 50000 | 50000 | 50000 | 50000 | 50000 | 50000 | 50000 | 50000 | 50000
PD-16 | C | Invasives Strategy (FY09-FY13) | 0 | 0 | 0 | 0 | 100000 | 0 | 100000 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | Complete from PRRIP budget standpoint. | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0
PD-18 | O | AMP-Related Equipment (FY09-FY19) | 0 | 0 | 0 | 0 | 140000 | 130697.22 | 50000 | 33419.07 | 55000 | 1983.66 | 66215 | 66000 | 66215 | 66000 | 75000 | 75000 | 75000 | 65160 | 72652.1 | 60470.91 | 95100 | Program per use costs for Headwaters equipment (truck, airboat, etc.) during 2019 field work. | 95000 | 95000 | 95000 | 95000 | 95000 | 95000 | 95000 | 95000 | 95000 | 95000 | 95000 | 95000 | 95000
PD-22 | O | Sediment Augmentation Implementation (FY14-FY19) |  | 0 |  | 0 |  | 0 |  | 0 |  | 0 |  | 0 |  | 0 | 400000 | 0 | 16131 | 25454.5 | 205397.45 | 66800 | 221000 | $150,000 for implementation; $71,000 for bathymetric LiDAR. | 221000 | 221000 | 221000 | 221000 | 221000 | 221000 | 221000 | 221000 | 221000 | 221000 | 221000 | 221000 | 221000
|  | Sub-Total | 150000 | 17295.15 | 1700000 | 1147418.65 | 1000000 | 320775.04 | 1470000 | 576955.28 | 888000 | 780562.46 | 855345 | 840352.98 | 1156665 | 479919.83 | 957080 | 335341.18 | 640595.99 | 488713.54 | 619877.95 | 391028.29 | 2534552 |  | 766000 | 766000 | 766000 | 916000 | 766000 | 766000 | 916000 | 766000 | 766000 | 766000 | 766000 | 766000 | 766000 | 10258000
Integrated Monitoring & Research Plan Activities
G-1 | O | LiDAR Implementation (FY09-FY19) | 0 | 0 | 260000 | 250000 | 0 | 0 | 0 | 0 | 75000 | 41000 | 118100 | 94150 | 118100 | 183100 | 118100 | 94100 | 170560 | 181239.5 | 367549.5 | 353380 | 147000 | June aerial photography, November aerial photography, November LiDAR. | 147000 | 147000 | 147000 | 147000 | 147000 | 147000 | 147000 | 147000 | 147000 | 147000 | 147000 | 147000 | 147000
G-2 | O | Aerial Photography (FY08-FY19) | 10000 | 10000 | 20000 | 10000 | 40000 | 20850 | 21000 | 22309.5 | 25000 | 22309.5
G-3 | C | Revise & Update Geomorphology Monitoring Protocol (FY07-FY08) | 27000 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 |  | 0 | 0 | 0 | Complete from PRRIP budget standpoint. | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0
G-4 | C | Develop Scope of Work for 2008 System-Level Geomorphic Monitoring | 7500 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | Complete from PRRIP budget standpoint. | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0
G-5 | O | Geomorphology/In-Channel Vegetation Monitoring (FY09-FY19) | 10000 | 0 | 95000 | 0 | 395000 | 380500 | 300000 | 320163 | 447500 | 414654.25 | 450000 | 511456.64 | 477738 | 517652.59 | 495000 | 472685.05 | 552076.85 | 493136.86 | 84774.47 | 0 | 166700 | Collection of bathymetric LiDAR data for all Platte River channels within the Associated Habitat Reach (AHR). | 167000 | 167000 | 167000 | 167000 | 167000 | 167000 | 167000 | 167000 | 167000 | 167000 | 167000 | 167000 | 167000
H-2 | O | Program Stream Gages (FY08-FY19) | 14500 | 6885 | 29500 | 20807.14 | 30000 | 23194.24 | 50000 | 47150.49 | 50000 | 32994.01 | 40000 | 28374.81 | 40000 | 18869.38 | 38000 | 36810.78 | 22620.17 | 22588.03 | 22644.4 | 18065.5 | 25000 | Stream gage operation and maintenance costs related to generating real-time discharge data related to Program activities. | 25000 | 25000 | 25000 | 25000 | 25000 | 25000 | 25000 | 25000 | 25000 | 25000 | 25000 | 25000 | 25000
H-4,5 | C | Unsteady Flow Model Calibration (FY07) | 23500 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | Complete from PRRIP budget standpoint. | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0
IMRP-1 | C | SDHF Monitoring (FY09-FY19) | 0 | 0 | 0 | 0 | 50000 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 80.6 | 0 | 0 | 0 | 0 | 0 | Complete from PRRIP budget standpoint. | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0
IMRP-2 | O | AMP Directed Research Projects (FY09-FY32) | 0 | 0 | 0 | 0 | 700000 | 93684.44 | 325000 | 38712.82 | 450000 | 221712.19 | 335000 | 172182.7 | 450000 | 308266.07 | 117000 | 143326.01 | 50828.94 | 98640.36 | 40813.18 | 19453.54 | 105000 | $75,000 for final year of grassland vegetation monitoring, $30,000 for final year of wet meadow research. | 100000 | 100000 | 100000 | 100000 | 100000 | 100000 | 100000 | 100000 | 100000 | 100000 | 100000 | 100000 | 100000
IMRP-3 | O | Adaptive Management Plan Special Advisors (FY10-FY32) | 0 | 0 | 0 | 0 | 0 | 0 | 150000 | 127732.32 | 150000 | 129371.6 | 140000 | 54460.53 | 50000 | 43575.89 | 75000 | 44987.98 | 72591.01 | 135438.11 | 83007.2 | 57101.38 | 200000 | Compass facilitation of AMP update process, advice on geomorphology and sediment. | 150000 | 150000 | 150000 | 150000 | 150000 | 150000 | 150000 | 150000 | 150000 | 150000 | 150000 | 150000 | 150000
IMRP-4 | C | FSM "Proof of Concept" Activities @ Elm Creek Complex (FY11-FY16) | 0 | 0 | 0 | 0 | 0 |  | 0 | 0 | 250000 | 248828.11 | 203185 | 200971.69 | 227835 | 268157.77 | 0 | 20551.51 | 4818.27 | 0 | 0 | 0 | 0 | Complete from PRRIP budget standpoint. | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0
IMRP-5 | C | FSM "Proof of Concept" Activities @ Shoemaker Island Complex (FY12-FY16) | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 250000 | 25098.27 | 245200 | 370571.41 | 319100 | 342057.01 | 286833.21 | 136873.92 | 75303.32 | 0 | 0 | Complete from PRRIP budget standpoint. | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0
IMRP-6 | O | Habitat Availability Analysis (FY11-FY19) | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 143227 | 20000 | 35000 | 147227 | 36000 | 0 | 43832 | 0 | 0 | 0 | 0 | Complete from PRRIP budget standpoint. | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0
PD-8 | O | Database Management System Development & Maintenance (FY08-FY19) | 150000 | 0 | 159000 | 125000 | 200000 | 72849.67 | 572150.33 | 453767.64 | 140000 | 154925.53 | 165615.18 | 151460.9 | 130000 | 109982.54 | 105000 | 113673.26 | 110339.72 | 125392.8 | 80387.26 | 296777.74 | 60000 | Program web site and species database maintenance and development. | 80000 | 80000 | 80000 | 80000 | 80000 | 80000 | 80000 | 80000 | 80000 | 80000 | 80000 | 80000 | 80000
PS-1 | C | Pallid Sturgeon Existing Information Review/Summary (FY08) | 32400 | 0 | 32400 | 30979.25 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | Complete from PRRIP budget standpoint. | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0
PS-2 | C | Lower Platte River Stage Change Study (FY08-FY09) | 200000 | 2336.36 | 200000 | 46458.42 | 182634.74 | 168195.1 | 54432.43 | 10633.5 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | Complete from PRRIP budget standpoint. | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0
PS-3 | O | Pallid Sturgeon Process (FY18-FY24) |  | 0 |  | 0 |  | 0 |  | 0 |  | 0 |  | 0 |  | 0 |  | 0 | 0 | 0 | 0 | 0 | 0 | Merged with AMP update process. | 620000 | 450000 | 450000 | 250000 | 620000 | 450000 | 450000 | 250000 | 250000 | 0 | 0 | 0 | 0
TP-1 | O | Tern & Plover Monitoring (FY08-FY32) | 14000 | 0 | 20000 | 0 | 100000 | 0 | 150000 | 52599.56 | 300000 | 210085.04 | 215000 | 233439.79 | 310000 | 266780.19 | 325000 | 301309.94 | 286555.69 | 177251.15 | 165199.48 | 76855.24 | 75000 | $72,000 for predator trapping, $3,000 for camera supplies. | 75000 | 75000 | 75000 | 75000 | 75000 | 75000 | 75000 | 75000 | 75000 | 75000 | 75000 | 75000 | 75000
TP-2 | C | Finish Forage Fish Monitoring Protocol (FY07-FY08) | 5000 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | Complete from PRRIP budget standpoint. | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0
TP-3 | C | Forage Fish Monitoring (FY08) | 5000 | 0 | 7500 | 0 | 50000 | 0 | 50000 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | Complete from PRRIP budget standpoint. | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0
TP-4 | C | Tern & Plover Foraging Habits Study (FY09-FY10) | 120000 | 0 | 40000 | 0 | 105000 | 100355.96 | 144644.04 | 139645.92 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | Complete from PRRIP budget standpoint. | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0
TP-5 | C | Analysis of CA-Collected Tern/Plover Monitoring Data (FY08) | 0 | 0 | 35000 | 37638.22 | 16035 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | Complete from PRRIP budget standpoint. | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0
WC-1 | O | Whooping Crane Monitoring (FY08-FY32) | 130000 | 126521.2 | 130000 | 111438.3 | 150000 | 135637.58 | 150000 | 132917.31 | 170000 | 186779.28 | 225091 | 208492.87 | 290000 | 261084.18 | 275000 | 268278.1 | 264492.78 | 223045.07 | 185215.16 | 223132.38 | 190000 | Contracted amount ($148,048) for 2019 spring monitoring/reporting and $42,000 for EDO to implement the monitoring protocol in fall 2019. | 100000 | 100000 | 100000 | 100000 | 100000 | 100000 | 100000 | 100000 | 100000 | 100000 | 100000 | 100000 | 100000
WC-2 | C | Analysis of CA-Collected Whooping Crane Monitoring Data (FY08) | 25000 | 32497.42 | 6454.48 | 6454.48 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | Complete from PRRIP budget standpoint. | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0
WC-3 | C | Whooping Crane Telemetry Tracking (FY09-FY17) | 0 | 0 | 125000 | 0 | 125000 | 125000 | 125000 | 125000 | 125000 | 41999.99 | 167100 | 143615.93 | 95000 | 61066.98 | 35500 | 29211.27 | 12260.49 | 8371.82 | 2663.38 | 1202.2 | 0 | Complete from PRRIP budget standpoint. | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0
WC-4 | C | Water Surface Estimation at Crane Use Sites (FY07-FY08) | 18312 | 4360 | 23120 | 23120 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | Complete from PRRIP budget standpoint. | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0
WC-5 | C | IGERT Whooping Crane Habitat Selection Project (FY12-FY13) | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 25000 | 18750 | 0 | 6250 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | Complete from PRRIP budget standpoint. | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0
WC-6 | O | Whooping Crane Stopover Site Evaluation Project (FY13-FY16) |  | 0 |  | 0 |  | 0 |  | 0 |  | 0 | 0 | 0 | 110297 | 91643.05 | 98608 | 70957.91 | 32854.21 | 33156.98 | 216.19 | 0 | 0 | Complete from PRRIP budget standpoint. | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0
WMV-1 | C | Vegetation Mapping Effort (FY07-FY08) | 25000 | 10334.4 | 14665 | 5196.36 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | Complete from PRRIP budget standpoint. | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0
WMV-2 | C | Wet Meadows Information Review and CEM Refinement (FY10) | 0 | 0 | 32400 | 0 | 50000 | 0 | 50000 | 0 | 0 | 50000 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | Complete from a PRRIP budget standpoint. | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0
WQ-1 | C | Water Quality Monitoring (FY09-FY11) | 0 | 0 | 40000 | 40000 | 184000 | 175043.2 | 188956.8 | 176747.3 | 280000 | 225022.39 | 150000 | 156084.25 | 152000 | 190263.4 | 0 | 43675.17 | 0 | 0 | 0 | 0 | 0 | Complete from PRRIP budget standpoint. | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0
|  | Sub-Total | 817212 | 192934.38 | 1270039.48 | 707092.17 | 2377669.74 | 1295310.19 | 2331183.6 | 1647379.36 | 2462500 | 1979681.89 | 2627318.18 | 2018538.38 | 2731170 | 2844490.45 | 2037308 | 1981704.59 | 1910663.34 | 1635134.6 | 1107773.54 | 1045967.98 | 968700 |  | 1464000 | 1294000 | 1294000 | 1094000 | 1464000 | 1294000 | 1294000 | 1094000 | 1094000 | 844000 | 844000 | 844000 | 844000 | 14762000
AMP Independent Science Review
ISAC-1 | O | ISAC Stipends & Expenses (FY09-FY19) | 80000 | 0 | 115000 | 0 | 142000 | 138306.72 | 150000 | 129192.27 | 185000 | 178034.77 | 185000 | 191375.02 | 221000 | 167400.31 | 200000 | 198733.44 | 159827.81 | 154432.48 | 143801.77 | 42996.91 | 200000 | Annual stipends, meeting expenses. Includes additional ISAC time and expenses for AMP update process. | 200000 | 200000 | 200000 | 200000 | 200000 | 200000 | 200000 | 200000 | 200000 | 200000 | 200000 | 200000 | 200000
ISAC-2 | C | Meetings, Expenses, etc. (FY08) | 0 | 0 | 5000 | 0 | 0 |  | 0 | 0 | 0 | 1250.93 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | Complete from PRRIP budget standpoint. | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0
ISAC-3 | C | Initial Establishment /Planning Session Expenses (FY08) | 0 | 0 | 5000 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | Complete from PRRIP budget standpoint. | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0
PD-3 | O | AMP & IMRP Peer Review (FY09-FY19) | 50000 | 0 | 105000 | 0 | 50000 | 49500 | 50000 | 0 | 115000 | 59845.5 | 90000 | 43046.75 | 108000 | 8940.75 | 318500 | 26492.8 | 94970 | 60507.5 | 3447.5 | 0 | 40000 | Wet meadow research peer review. | 40000 | 60000 | 60000 | 60000 | 60000 | 60000 | 60000 | 60000 | 60000 | 60000 | 60000 | 60000 | 60000
PD-11 | O | AMP Reporting (FY09-FY19) | 0 | 0 | 10000 | 0 | 10000 | 0 | 70000 | 24340.91 | 25000 | 7192.33 | 25000 | 11399.38 | 25000 | 13162.07 | 14000 | 9137.62 | 13634.83 | 6824.05 | 5650.14 | 11660.05 | 15000 | Estimated meeting costs for AMP Reporting Session in fall 2019 in Omaha, NE. | 10000 | 10000 | 10000 | 10000 | 10000 | 10000 | 10000 | 10000 | 10000 | 10000 | 10000 | 10000 | 10000
PD-21 | O | PRRIP Publications (FY14-FY19) | [12 empty] | 0 | 0 | 20000 | 18977.4 | 7445.1 | 3300 | 7073 | 2500 | 9000 | Publication of inside versus outside LTPP monitoring and two undetermined publications. | 15000 | 6000 | 6000 | 6000 | 6000 | 6000 | 6000 | 6000 | 6000 | 6000 | 6000 | 6000 | 6000
|  | Sub-Total | 130000 | 0 | 240000 | 0 | 202000 | 187806.72 | 270000 | 153533.18 | 325000 | 246323.53 | 300000 | 245821.15 | 354000 | 189503.13 | 552500 | 253341.26 | 275877.74 | 225064.03 | 159972.41 | 57156.96 | 264000 |  | 265000 | 276000 | 276000 | 276000 | 276000 | 276000 | 276000 | 276000 | 276000 | 276000 | 276000 | 276000 | 276000 | 3577000
|  | AMP Sub-Total | 1172212 | 219829.08 | 3285039.48 | 1903536.54 | 4369669.74 | 1913374.83 | 5191974.81 | 3128430.7 | 4435500 | 3465520.73 | 4897551.18 | 3872945.24 | 5068239 | 4360925.61 | 3546888 | 2845167.33 | 2827137.07 | 2348912.17 | 1887623.9 | 1494153.23 | 3787252 | 34054808.43 | 2515000 | 2356000 | 2336000 | 2286000 | 2506000 | 2336000 | 2486000 | 2136000 | 2136000 | 1906000 | 1906000 | 1906000 | 1906000 | 28717000
|  |  | Column A | Column A | Column C | Column B | Column E | Column C | Column G | Column D | Column I | Column E | Column F | Column F | Column H | Column G | Column J | Column H | Column I | Column J | Column K | Column L | Column M | Estimated First Increment Total ($187M available in 2005 dollars) | Column O | Column P | Column Q | Column R | Column S | Column T | Column U | Column V | Column W | Column X | Column Y | Column Z | Column AA | 171786500
PRRIP BUDGET TOTALS |  |  | 2434261 | 1058592.22 | 11053964 | 3559179.93 | 16326458.24 | 13587723.45 | 17834817.71 | 10245625.14 | 19630000 | 9430963.7 | 25223351.18 | 15877903.97 | 27100139 | 23427321.98 | 25351911 | 7400874.72 | 8371405.7 | 10461413.98 | 13214962.14 | 7647497.78 | 27913527 | 152196991.71 | 21319500 | 15038500 | 12678500 | 12628500 | 12563500 | 12528500 | 12578500 | 12228500 | 12228500 | 11998500 | 11998500 | 11998500 | 11998500 | 171786500
Status Label |  | * All budget numbers in 2005 dollars | [21 empty] | 152196991.71
O = Ongoing, N = New, C = Complete
34803008.29
AMP Project ID Labels:
G = Geomorphology
H = Hydrology
IMRP = Integrated Monitoring and Research Plan
PD = General Activities/Program Development
PS = Pallid Sturgeon
TP = Terns/Plovers
WC = Whooping Cranes
WMV = Wet Meadows/Vegetation
WQ = Water Quality