## 2015 PRRIP Budget
PRRIP Project ID | Status | PRRIP Project Description | FY 2007 Final Budget | FY 2007 Expenditures | FY 2008 Budget (New Money + FY 2007 UO) | FY 2008 Expenditures | FY 2009 Budget (New Money + FY 2008 UO) | FY 2009 Expenditures | FY 2010 Budget (New Money + FY 2009 UO) | FY 2010 Expenditures | FY 2011 Budget (New Money) | FY 2011 Expenditures | FY 2012 Budget (New Money) | FY 2012 Expenditures | FY2013 Budget (New Money) | FY 2013 Expenditures | FY 2014 Approved Budget | FY 2014 Expenditures (as of 11-20-14) | FY 2015 Budget New Money (estimated) | "Quick Reference" Comments on FY 2015 Estimated New Money Budget Numbers (see FY 2015 Work Plan for Full Description) | FY 2016 Estimated New Money | FY 2017 Estimated New Money | FY 2018 Estimated New Money | FY 2019 Estimated New Money
|  |  | Column A | Column A | Column C | Column B | Column E | Column C | Column G | Column D | Column I | Column E | Column F | Coulumn F | Column H | Column G | Column H | Column I | Column J | Column K | Column L | Column M | Column N | Column O
Executive Director's Office (ED)
ED-1 | O | Salaries/Travel/Office Expenditures (FY08-FY19) | 192688 | 210292.78 | 1110600 | 1220138.33 | 1427759 | 1535891.24 | 1599900 | 1650847.94 | 1600000 | 1725903.82 | 1800000 | 1845945.69 | 1875000 | 1903370.23 | 2200000 | 1704878.7 | 2200000 | Salaries, travel, and other direct costs associated with ED and staff in ED Office | 2200000 | 2200000 | 2200000 | 2200000
ED-2 | O | Administrative and Other Support Services (FY08-FY19) | 411861 | 348673.3 | 170614.52 | 87493.91 | 250000 | 156323.84 | 200000 | 88096.51 | 200000 | 152262.3 | 150000 | 172961.05 | 150000 | 63318.9 | 100000 | 57563.24 | 100000 | Public notices, land and water specialty attorneys, and other miscellaneous services required to support ED efforts | 100000 | 100000 | 100000 | 100000
ED-3 | O | Public Outreach (FY09-FY19) | 0 | 0 | 0 | 0 | 30000 | 30310.63 | 40000 | 32606.7 | 50000 | 50381.58 | 70000 | 70335.38 | 65000 | 64973.54 | 60000 | 57606.5 | 75000 | Exhibit fees, major sponsorships, other sponsorships, promotional materials | 70000 | 75000 | 70000 | 75000
|  | Sub-Total | 604549 | 558966.08 | 1281214.52 | 1307632.24 | 1707759 | 1722525.71 | 1839900 | 1771551.15 | 1850000 | 1928547.7 | 2020000 | 2089242.12 | 2090000 | 2031662.67 | 2360000 | 1820048.44 | 2375000 | 25095176.11 | 2370000 | 2375000 | 2370000 | 2375000
Governance Committee/Finance Committee (GFC)
GFC-1 | O | NCF Fees (FY08-FY19) | 75000 | 22147.61 | 100000 | 77178.48 | 255000 | 235881.2 | 260000 | 206470.89 | 300000 | 195565.15 | 450000 | 327323.13 | 450000 | 414896.52 | 250000 | 69764.12 | 290000 | Annual fees for Financial Management Entity; assumes expenditures about $25 million. | 250000 | 125000 | 125000 | 125000
GFC-2 | O | Pulse Flow and Other Insurance (FY08-FY19) | 100000 | 2448.21 | 50000 | 41834 | 60000 | 56394 | 70000 | 62632 | 75000 | 69026 | 70000 | 64870.55 | 75000 | 74531 | 75000 | 77212 | 80000 | Program insurance for pulse flow and liability; insurance for vehicles and liability for airboat now on Headwaters | 80000 | 80000 | 80000 | 80000
GFC-3 | O | Expenses, Meeting Rooms, etc. (FY08-FY19) | 5000 | 1001.82 | 5000 | 1500.12 | 5000 | 3378.95 | 5000 | 499.92 | 1000 | 2720.26 | 1500 | 9269.33 | 1500 | 3126.35 | 1700 | 3405.06 | 3100 | Expenses associated with GC meetings outside of Kearney | 3100 | 3100 | 3100 | 3100
GFC-4 | O | SDHF Reserve (FY09-FY19) | 0 | 0 | 0 | 0 | 1000000 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | Annual reserve for potential EA bypass-related costs | 0 | 0 | 0 | 0
|  | Sub-Total | 180000 | 25597.64 | 155000 | 120512.6 | 1320000 | 295654.15 | 335000 | 269602.81 | 376000 | 267311.41 | 521500 | 401463.01 | 526500 | 492553.87 | 326700 | 150381.18 | 373100 | 3353576.67 | 333100 | 208100 | 208100 | 208100
Program Advisory Committees
LAC-1 | O | Expenses, Meeting Rooms, etc. (FY08-FY19) | 7500 | 201.36 | 7500 | 414.04 | 7500 | 245.56 | 7500 | 0 | 1000 | 785.4 | 1500 | 1283.14 | 2000 | 921.36 | 1600 | 555.28 | 1100 | Conference line charges for LAC meetings; other associated costs | 1100 | 1100 | 1100 | 1100
WAC-1 | O | Expenses, Meeting Rooms, etc. (FY08-FY19) | 5000 | 0 | 5000 | 23.56 | 5000 | 0 | 5000 | 0 | 1000 | 2330.9 | 1500 | 5457.54 | 6000 | 1731.62 | 3500 | 897.6 | 2700 | Conference line charges for WAC meetings; other associated costs | 2700 | 2700 | 2700 | 2700
TAC-1 | O | Expenses, Meeting Rooms, etc. (FY08-FY19) | 5000 | 820 | 5000 | 75 | 5000 | 864.3 | 5000 | 0 | 1000 | 1231.56 | 1500 | 2246.87 | 4000 | 2436.72 | 2400 | 889.62 | 2000 | Conference line charges for TAC meetings; other associated costs | 2000 | 2000 | 2000 | 2000
|  | Sub-Total | 17500 | 1021.36 | 17500 | 512.6 | 17500 | 1109.86 | 17500 | 0 | 3000 | 4347.86 | 4500 | 8987.55 | 12000 | 5089.7 | 7500 | 2342.5 | 5800 | 52411.43 | 5800 | 5800 | 5800 | 5800
Land Plan Implementation (LP)
- | C | Land Interest Holding Entity Negotiations & Start-Up (FY07) | 10000 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | Complete from PRRIP budget standpoint | 0 | 0 | 0 | 0
LP-3 | O | Land Acquisition (FY09-FY19) | 0 | 0 | 6000000 | 57235.61 | 7000000 | 8875890.01 | 6000000 | 3335269.11 | 5000000 | 2108612.42 | 5000000 | 6395100.41 | 3000000 | 875844.32 | 1500000 | 247977.31 | 1535000 | Land acquisition costs for balance of Palustrine Wetland acres; annual LIHE fees and property taxes. | 500000 | 500000 | 300000 | 300000
LP-4 | O | Land Management (FY09-FY19) | 0 | 0 | 0 | 0 | 500000 | 116216.05 | 588800 | 587818.14 | 365500 | 366316.52 | 409800 | 314190.47 | 448400 | 282723.31 | 192500 | 239844.14 | 309100 | Basic land operations and maintenance including road, fence, and building upkeep, noxious weed control, mowing, etc. Agricultural input costs for share cropping agreements including seed, fertilizer and herbicide application, crop insurance, etc. Based on actual work bids for 2014 rates. | 310000 | 310000 | 310000 | 310000
LP-5 | C | Cottonwood Ranch Bridge Final Design & Construction (FY10) | 0 | 0 | 0 | 0 | 0 | 25576.24 | 250000 | 48087.64 | 250000 | 171130.79 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | Complete from PRRIP budget standpoint | 0 | 0 | 0 | 0
LP-6 | O | Land Plan Special Advisors (FY10-FY19) | 0 | 0 | 0 | 0 | 0 | 0 | 50000 | 59115.02 | 150000 | 48726.16 | 120000 | 15717.64 | 50000 | 19105.45 | 20000 | 0 | 20000 | Land-related specialty items such as land leases, Farm Service Agency (FSA) reporting, and rent collections on all complex and non-complex properties. Advisors shall continue annually on all land to the end of the First Increment. 2015 numbers based on projected 2014 actual costs. | 20000 | 20000 | 20000 | 20000
LP-7 | O | Public Access Management (FY11-FY19) | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 50000 | 50000 | 50000 | 50000 | 55000 | 50065 | 50000 | 1388.5 | 50000 | Nebraska Game and Parks Commission is the contracted provider. | 50000 | 50000 | 50000 | 50000
|  | Sub-Total | 10000 | 0 | 6000000 | 57235.61 | 7500000 | 9017682.3 | 6888800 | 4030289.91 | 5815500 | 2744785.89 | 5579800 | 6775008.52 | 3553400 | 1227738.08 | 1762500 | 489209.95 | 1914100 | 29376050.26 | 880000 | 880000 | 680000 | 680000
Water Plan Implementation (WP)
WP-1(a) | O | Active Channel Capacity Improvements (N. Platte Channel above CNPPID Diversion Dam) (FY07-FY17) | 241000 | 110690.94 | 153210 | 10805.5 | 161529.5 | 149886.6 | 61642.9 | 36104.18 | 250000 | 36789.63 | 100000 | 28297.28 | 500000 | 180167.27 | 260000 | 16056.72 | 240000 | Efforts to increase North Platte River channel capacity including flood-risk reduction projects, vegetation clearing/disking and canal by-pass projects | 1000000 | 1000000 | 0 | 0
WP-1(b) | O | Active Channel Capacity Improvements (CNPPID Diversion Dam to Grand Island) (FY10-FY19) | 0 | 0 | 0 | 0 | 0 | 0 | 400000 | 400000 | 200000 | 200000 | 200000 | 200000 | 200000 | 200000 | 100000 | 100000 | 200000 | In-channel maintenance effort associated with the NET Grant Application for the Platte River Management and Enhancement; joint project effort with the NRDs, Program and other participants | 200000 | 200000 | 200000 | 200000
WP-2(a) | C | Water Management Study Phase 1 (FY07-FY08) | 124000 | 119016.12 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | Complete from PRRIP budget standpoint | 0 | 0 | 0 | 0
WP-2(b) | C | Water Management Study Phase II (FY08) | 0 | 0 | 157000 | 155969.84 | 0 | 0 | 0 | 0 | 0 |  | 0 | 0 | 0 | 0 | 0 | 0 | 0 | Complete from PRRIP budget standpoint | 0 | 0 | 0 | 0
WP-3 | C | Test Flow Routing Model/2008 EA Augmented SDHF Pilot Study (FY09) | 75000 | 23471 | 0 | 0 | 0 | 65678.08 | 0 | 0 | 0 |  | 0 | 0 | 0 | 0 | 0 | 0 | 0 | Complete from PRRIP budget standpoint | 0 | 0 | 0 | 0
WP-4(a) | O | Water Action Plan (J2 Rereg Reservoir) (FY09-FY19) | 0 | 0 | 0 | 0 | 250000 | 29272.57 | 0 | 0 | 5100000 | 0 | 9000000 | 223820.22 | 13000000 | 14612380.23 | 14392000 | 0 | 14392000 | Reservoir construction cost (3-year budget from 2015-2017); construction anticipated in 2018 | 14392000 | 14392000 | 250000 | 250000
WP-4(b) | O | Water Action Plan (CNPPID system groundwater projects) (FY15-FY19) |  | 0 |  | 0 |  | 0 |  | 0 |  | 0 |  | 6790.86 |  | 151050 | 88296 | 0 | 310146.02 | Phelps Cty Canal groundwater recharge project and groundwater recharge pumping project included in this line item | 165930.92 | 172116.42 | 178605.47 | 185414.4
WP-4(c)i | C | No Cost NCCW | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 1500000 | 0 | 26250 | 0 | 0 | Complete from PRRIP budget standpoint | 0 | 0 | 0 | 0
WP-4(c)ii | O | Purchased NCCW | [12 empty] | 0 | 0 | 0 | 0 | 0 | Not anticipated at this time. | 0 | 0 | 0 | 0
WP-4(d) | C | Water Action Plan (Pathfinder Municipal Accnt) (FY12) | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 2000000 | 1958400 | 0 | 0 | 0 | 0 | 0 | Complete from PRRIP budget standpoint | 0 | 0 | 0 | 0
WP-4(e) | O | Water Action Plan (CO GW Mgmnt) (FY16-FY19) | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 1854667 | 0 | 0 | Out-year costs only. | 569620.25 | 569620.25 | 569620.25 | 569620.25
WP-4(f)i | O | Water Action Plan (CPNRD surface & groundwater leasing & acquisition) (FY15-FY19) | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 500000 | 0 | 150000 | 34156.5 | 0 | 0 | 1035137.84 | Lease with the CPNRD for transferred surface water rights (consumptive use portion) and groundwater recharge accretions from excess flows. Permanent acquisition of 40 AF of surface water from irrigator in CPNRD. | 959929.43 | 996292.58 | 1034314.01 | 1074086.03
WP-4(f)ii | O | Water Action Plan (NPPD leasing) (FY15-FY19) |  | 0 |  | 0 |  | 0 |  | 0 |  | 0 |  | 0 | 0 | 0 | 0 | 0 | 147663.96 | Potential lease with the NPPD for transferred relinquished surface water rights. Budget includes cost for offset water to mitigate depletions from groundwater irrigation on lands. | 138557.55 | 143391.51 | 148399.31 | 153589.35
WP-4(f)iii | O | Water Action Plan (CNPPID leasing-storage) (FY15-FY19) |  | 0 |  | 0 |  | 0 |  | 0 |  | 0 |  | 0 | 0 | 0 | 148750 | 0 | 625000 | Potential lease with the CNPPID for storage water in Lake McConaughy; estimated volume of 2,500 AF. | 910000 | 946400 | 1406080 | 1462323.2
WP-4(f)iv | O | Water Action Plan (CNPPID leasing-irrigator) (FY15-FY19) |  | 0 |  | 0 |  | 0 |  | 0 |  | 0 |  | 0 |  | 0 | 198360 | 0 | 385111.72 | Surface water leases with irrigators in the CNPPID system. Water available in Lake McConaughy; estimated volume of 2,500 AF. Includes budget to offset increased depletions from groundwater irrigation on lands. | 561218.14 | 584199.5 | 781894.36 | 904403.78
WP-4(f)v | O | Water Action Plan (NPNRD leasing) (FY15-FY19) |  | 0 |  | 0 |  | 0 |  | 0 |  | 0 |  | 0 |  | 0 | 0 | 0 | 390000 | Potential leases with irrigators in the North Platte NRD; estimated volume of 1,950 AF. Assumes irrigators switch to dry land farming or "dry up" their land. | 721000 | 742630 | 983454.3 | 1125508.81
WP-4(g) | O | Water Action Plan (Water Mgmnt Incentives) (FY17-FY19) | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | Out-year costs only. | 0 | 600000 | 600000 | 600000
WP-4(h) | O | Water Action Plan (NE GW Mgmnt) (FY12-FY19) | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 100000 | 0 | 250000 | 47091.78 |  | 0 | 0 | No projects anticipated at this time | 0 | 0 | 0 | 0
WP-5 | O | Management Tool (FY12-FY17) | 0 | 0 | 0 | 0 | 0 | 0 | 100000 | 0 | 200000 | 0 | 50000 | 0 | 50000 | 3520.71 | 90000 | 5175.8 | 129600 | COHYST model upgrades, time period extension, GUI development, technical oversight and training. | 100000 | 90000 | 0 | 0
WP-6 | C | Feasibility Studies (FY09-FY12) | 0 | 0 | 0 | 0 | 500000 | 392539.35 | 2050000 | 486884.73 | 600000 | 625483.22 | 0 | 133455.96 | 0 | 0 | 0 | 0 | 0 | Complete from PRRIP budget standpoint | 0 | 0 | 0 | 0
WP-7 | C | Water Acquisition (FY09-FY11) | 0 | 0 | 0 | 0 | 500000 | 0 | 500000 | 0 | 300000 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | Complete from PRRIP budget standpoint | 0 | 0 | 0 | 0
WP-8 | O | Water Plan Special Advisors (FY10-FY19) | 0 | 0 | 0 | 0 | 0 | 0 | 150000 | 92651.89 | 200000 | 141029.41 | 150000 | 143385.55 | 125000 | 58984.48 | 100000 | 33945.65 | 100000 | Advisors on water-related specialty topics such as economics, hydro-geology/ground water, structural, and water project permitting. | 100000 | 100000 | 50000 | 50000
WP-9 | O | Miscellaneous Water Resources Studies (FY15) | 0 | 0 | 0 | 0 | 0 | 0 | 200000 | 30109.77 | 100000 | 17147.85 | 50000 | 36107.66 | 25000 | 0 | 0 | 0 | 25000 | Refinement of the North Platte River basin and South Platte River basin studies to utilize hydroclimatic indices to forecast spring streamflows. | 0 | 0 | 0 | 0
- | C | Legal Review for North Platte Channel Capacity Project (FY08) | 10000 | 0 | 5000 | 2975 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | Complete from PRRIP budget standpoint | 0 | 0 | 0 | 0
|  | Sub-Total | 450000 | 253178.06 | 315210 | 169750.34 | 1411529.5 | 637376.6 | 3461642.9 | 1045750.57 | 6950000 | 1020450.11 | 12150000 | 2730257.53 | 15800000 | 15287350.97 | 17258323 | 155178.17 | 17979659.54 | 92411171.96 | 19818256.29 | 20536650.26 | 6202367.7 | 6574945.82
AMP Experimental Design
PD-4 | C | AMP Workshops (FY09-FY13) | 50000 | 9599.55 | 75000 | 49025.72 | 10000 | 274.09 | 10000 | 0 | 10000 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | Complete from PRRIP budget standpoint | 0 | 0 | 0 | 0
PD-12 | C | Model Application (FY09-FY13) | 0 | 0 | 0 | 0 | 360000 | 0 | 390000 | 348094.61 | 150000 | 177467.55 | 20000 | 0 | 10000 | 1997.1 | 0 | 0 | 0 | Complete from PRRIP budget standpoint | 0 | 0 | 0 | 0
PD-13 | C | Sediment Augmentation Feasibility Analysis, Design, and Permitting (FY09-FY13) | 0 | 0 | 0 | 0 | 400000 | 89208.79 | 520791.21 | 320791.21 | 350000 | 145831.72 | 540888 | 505117.78 | 671404 | 681104.94 | 0 | 237060.3 | 0 | Complete from PRRIP budget standpoint | 0 | 0 | 0 | 0
PD-14 | C | Whooping Crane Conservation Action Plan (CAP) Development (FY09) | 0 | 0 | 0 | 0 | 20000 | 20000 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | Complete from PRRIP budget standpoint | 0 | 0 | 0 | 0
PD-19 | C | Flow Consolidation Conceptual Design (FY10-FY13) | 0 | 0 | 0 |  | 0 | 0 | 200000 | 81677.06 | 200000 | 104277.64 | 230000 | 59500.76 | 100000 | 43042.6 | 0 | 37720 | 0 | Complete from PRRIP budget standpoint | 0 | 0 | 0 | 0
PD-20 | C | Wet Meadow Restoration on Tract 2009001 (FY11-FY13) | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 50000 | 31375.94 | 324000 | 203614.19 | 45000 | 120867.56 | 0 | 0 | 0 | Complete from PRRIP budget standpoint | 0 | 0 | 0 | 0
- | C | Develop Mgmt.-Level Hypothesis Testing for FSM/Clear-Level Plow (FY07) | 25000 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | Complete from PRRIP budget standpoint | 0 | 0 | 0 | 0
|  | Sub-Total | 75000 | 9599.55 | 75000 | 49025.72 | 790000 | 109482.88 | 1120791.21 | 750562.88 | 760000 | 458952.85 | 1114888 | 768232.73 | 826404 | 847012.2 | 0 | 274780.3 | 0 |  | 0 | 0 | 0 | 0
AMP Implementation Activities
- | C | AMWG Assistance & Operating Expenses | 0 | 13620.15 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | Complete from PRRIP budget standpoint | 0 | 0 | 0 | 0
LP-2 | O | FSM/MCM Actions at Habitat Complexes (FY08-FY19) | 25000 | 3675 | 0 | 0 | 350000 | 187879.35 | 1270000 | 493536.21 | 483000 | 650585.59 | 639130 | 744190.85 | 890450 | 333469.4 | 432080 | 264722.99 | 773490 | General actions at habitat complexes; see FY15 Annual Land Work Plan for specific details | 300000 | 300000 | 300000 | 100000
LP-2(a) | C | Cottonwood Ranch Maintenance & Enhancement (FY07-FY08) | 75000 | 0 | 550000 | 251710.1 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | Complete from PRRIP budget standpoint | 0 | 0 | 0 | 0
LP-2(b) | C | Pre-2007 Cottonwood Ranch Maintenance & Enhancement (FY08) | 0 | 0 | 850000 | 848836.22 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | Complete from PRRIP budget standpoint | 0 | 0 | 0 | 0
WP-10 | O | Environmental Account SDHF (FY08-FY19) | 0 | 0 | 250000 | 46872.33 | 350000 | 2198.47 | 0 | 0 | 150000 | 0 | 0 | 0 | 150000 | 42940 | 0 | 0 | 0 | No SDMF planned in 2015 | 150000 | 0 | 150000 | 0
PD-7 | C | Program Anchor Points (FY09) | 50000 | 0 | 50000 | 0 | 50000 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | Complete from PRRIP budget standpoint | 0 | 0 | 0 | 0
PD-15 | O | AMP Permits (FY09-FY19) | 0 | 0 | 0 | 0 | 10000 | 0 | 50000 | 50000 | 200000 | 127993.21 | 150000 | 30162.13 | 50000 | 31287.93 | 50000 | 0 | 50000 | Estimate based on FY14 budget line item; contractor secured in FY14, assistance with permitting for island building, sediment augmentation (mechanical), and wetland restoration | 20000 | 20000 | 0 | 0
PD-16 | C | Invasives Strategy (FY09-FY13) | 0 | 0 | 0 | 0 | 100000 | 0 | 100000 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | Complete from PRRIP budget standpoint | 0 | 0 | 0 | 0
PD-18 | O | AMP-Related Equipment (FY09-FY19) | 0 | 0 | 0 | 0 | 140000 | 130697.22 | 50000 | 33419.07 | 55000 | 1983.66 | 66215 | 66000 | 66215 | 66000 | 75000 | 62500 | 75000 | Program per use costs for Headwaters equipment (truck, airboat, etc.) during 2015 field work. | 75000 | 75000 | 75000 | 75000
PD-22 | O | Sediment Augmentation Implementation (FY14-FY19) |  | 0 |  | 0 |  | 0 |  | 0 |  | 0 |  | 0 |  | 0 | 400000 | 0 | 370000 | $270,000 for implementation; $100,000 for monitoring and reporting; dependent on GC direction and securing COE permits; bid package for augmentation; assumes basic implementation of mechanical manipulation (not sand pumping) and monitoring | 400000 | 400000 | 400000 | 400000
|  | Sub-Total | 150000 | 17295.15 | 1700000 | 1147418.65 | 1000000 | 320775.04 | 1470000 | 576955.28 | 888000 | 780562.46 | 855345 | 840352.98 | 1156665 | 473697.33 | 957080 | 327222.99 | 1268490 |  | 945000 | 795000 | 925000 | 575000
Integrated Monitoring & Research Plan Activities
G-1 | O | LiDAR Implementation (FY09-FY19) | 0 | 0 | 260000 | 250000 | 0 | 0 | 0 | 0 | 75000 | 41000 | 118100 | 94150 | 118100 | 183100 | 118100 | 53100 | 125000 | June aerial photography, November aerial photography, November LiDAR from Kucera. | 125000 | 125000 | 125000 | 125000
G-2 | O | Aerial Photography (FY08-FY19) | 10000 | 10000 | 20000 | 10000 | 40000 | 20850 | 21000 | 22309.5 | 25000 | 22309.5
G-3 | C | Revise & Update Geomorphology Monitoring Protocol (FY07-FY08) | 27000 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | Complete from PRRIP budget standpoint | 0 | 0 | 0 | 0
G-4 | C | Develop Scope of Work for 2008 System-Level Geomorphic Monitoring | 7500 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | Complete from PRRIP budget standpoint | 0 | 0 | 0 | 0
G-5 | O | Geomorphology/In-Channel Vegetation Monitoring (FY09-FY19) | 10000 | 0 | 95000 | 0 | 395000 | 380500 | 300000 | 320163 | 447500 | 414654.25 | 450000 | 511456.64 | 477738 | 517652.59 | 495000 | 442167.35 | 512990 | Implementation of system-scale geomorphology and vegetation monitoring protocol, data analysis, and reporting. | 495000 | 495000 | 495000 | 495000
H-2 | O | Program Stream Gages (FY08-FY19) | 14500 | 6885 | 29500 | 20807.14 | 30000 | 23194.24 | 50000 | 47150.49 | 50000 | 32994.01 | 40000 | 28374.81 | 40000 | 18869.38 | 38000 | 32333.12 | 38000 | $18,000 for USGS (two gages on CWR through agreement with NPPD); $10,000 for Nebraska DNR (two gages at Shelton and Lexington); $10,000 for cost-share with CNPPID to continue real-time data at Overton through agreement with USGS for one more year. | 38000 | 38000 | 38000 | 38000
H-4,5 | C | Unsteady Flow Model Calibration (FY07) | 23500 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | Complete from PRRIP budget standpoint | 0 | 0 | 0 | 0
IMRP-1 | C | SDHF Monitoring (FY09-FY19) | 0 | 0 | 0 | 0 | 50000 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 80.6 | 0 | Complete from PRRIP budget standpoint | 0 | 0 | 0 | 0
IMRP-2 | O | AMP Directed Research Projects (FY09-FY19) | 0 | 0 | 0 | 0 | 700000 | 93684.44 | 325000 | 38712.82 | 450000 | 221712.19 | 335000 | 172182.7 | 450000 | 308266.07 | 117000 | 130126.01 | 71000 | Continued work on wet meadow hydrology project. | 100000 | 100000 | 100000 | 100000
IMRP-3 | O | Adaptive Management Plan Special Advisors (FY10-FY19) | 0 | 0 | 0 | 0 | 0 | 0 | 150000 | 127732.32 | 150000 | 129371.6 | 140000 | 54460.53 | 50000 | 43575.89 | 75000 | 32041.5 | 100000 | Assistance with expertise on geomorphology. | 100000 | 100000 | 100000 | 100000
IMRP-4 | C | FSM "Proof of Concept" Activities @ Elm Creek Complex (FY11-FY15) | 0 | 0 | 0 | 0 | 0 |  | 0 | 0 | 250000 | 248828.11 | 203185 | 200971.69 | 227835 | 268157.77 | 0 | 20551.51 | 0 | Complete from PRRIP budget standpoint | 0 | 0 | 0 | 0
IMRP-5 | O | FSM "Proof of Concept" Activities @ Shoemaker Island Complex (FY12-FY16) | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 250000 | 25098.27 | 245200 | 340614.92 | 319100 | 339895.64 | 403700 | Year 3 of implementation | 0 | 0 | 0 | 0
IMRP-6 | O | Habitat Availability Analysis (FY11-FY19) | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 143227 | 20000 | 35000 | 147227 | 36000 | 0 | 40000 | New money for analyses of FY14 data | 40000 | 40000 | 40000 | 40000
PD-8 | O | Database Management System Development & Maintenance (FY08-FY19) | 150000 | 0 | 159000 | 125000 | 200000 | 72849.67 | 572150.33 | 453767.64 | 140000 | 154925.53 | 165615.18 | 151460.9 | 130000 | 109982.54 | 105000 | 106158.97 | 110000 | Ongoing database development and management by Riverside Technologies | 110000 | 110000 | 110000 | 110000
PS-1 | C | Pallid Sturgeon Existing Information Review/Summary (FY08) | 32400 | 0 | 32400 | 30979.25 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | Complete from PRRIP budget standpoint | 0 | 0 | 0 | 0
PS-2 | C | Lower Platte River Stage Change Study (FY08-FY09) | 200000 | 2336.36 | 200000 | 46458.42 | 182634.74 | 168195.1 | 54432.43 | 10633.5 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | Complete from PRRIP budget standpoint | 0 | 0 | 0 | 0
TP-1 | O | Tern & Plover Monitoring (FY08-FY19) | 14000 | 0 | 20000 | 0 | 100000 | 0 | 150000 | 52599.56 | 300000 | 210085.04 | 215000 | 233439.79 | 310000 | 266780.19 | 325000 | 235033.33 | 280000 | Estimate for 2015 monitoring, analysis, and reporting. Will hire new contractor via competitive selection process in early 2015. | 280000 | 280000 | 280000 | 280000
TP-2 | C | Finish Forage Fish Monitoring Protocol (FY07-FY08) | 5000 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | Complete from PRRIP budget standpoint | 0 | 0 | 0 | 0
TP-3 | C | Forage Fish Monitoring (FY08) | 5000 | 0 | 7500 | 0 | 50000 | 0 | 50000 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | Complete from PRRIP budget standpoint | 0 | 0 | 0 | 0
TP-4 | C | Tern & Plover Foraging Habits Study (FY09-FY10) | 120000 | 0 | 40000 | 0 | 105000 | 100355.96 | 144644.04 | 139645.92 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | Complete from PRRIP budget standpoint | 0 | 0 | 0 | 0
TP-5 | C | Analysis of CA-Collected Tern/Plover Monitoring Data (FY08) | 0 | 0 | 35000 | 37638.22 | 16035 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | Complete from PRRIP budget standpoint | 0 | 0 | 0 | 0
WC-1 | O | Whooping Crane Monitoring (FY08-FY19) | 130000 | 126521.2 | 130000 | 111438.3 | 150000 | 135637.58 | 150000 | 132917.31 | 170000 | 186779.28 | 225091 | 208492.87 | 290000 | 260171.18 | 275000 | 229936.71 | 310000 | WEST/AIM contracted to conduct WC monitoring activities through spring 2015. Estimate for spring and fall monitoring, data analysis, and reporting. New contractor hired through competitive selection process for monitoring in fall 2015 and beyond. | 310000 | 310000 | 310000 | 310000
WC-2 | C | Analysis of CA-Collected Whooping Crane Monitoring Data (FY08) | 25000 | 32497.42 | 6454.48 | 6454.48 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | Complete from PRRIP budget standpoint | 0 | 0 | 0 | 0
WC-3 | O | Whooping Crane Telemetry Tracking (FY09-FY16) | 0 | 0 | 125000 | 0 | 125000 | 125000 | 125000 | 125000 | 125000 | 41999.99 | 167100 | 143615.93 | 95000 | 57856.8 | 35500 | 22631.6 | 23500 | As per WC Tracking Project Partnership Agreement budget; costs for data-download and data-management costs. | 11400 | 0 | 0 | 0
WC-4 | C | Water Surface Estimation at Crane Use Sites (FY07-FY08) | 18312 | 4360 | 23120 | 23120 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | Complete from PRRIP budget standpoint | 0 | 0 | 0 | 0
WC-5 | C | IGERT Whooping Crane Habitat Selection Project (FY12-FY13) | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 25000 | 18750 | 0 | 6250 | 0 | 0 | 0 | Complete from PRRIP budget standpoint | 0 | 0 | 0 | 0
WC-6 | O | Whooping Crane Stopover Site Evaluation Project (FY13-FY15) |  | 0 |  | 0 |  | 0 |  | 0 |  | 0 | 0 | 0 | 110297 | 91643.05 | 98608 | 14854.11 | 98608 | Program contribution for third year of a three-year contract with USGS for a research study to evaluate habitat metrics at whooping crane stopover sites from northern Texas - North Dakota. | 0 | 0 | 0 | 0
WMV-1 | C | Vegetation Mapping Effort (FY07-FY08) | 25000 | 10334.4 | 14665 | 5196.36 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | Complete from PRRIP budget standpoint | 0 | 0 | 0 | 0
WMV-2 | C | Wet Meadows Information Review and CEM Refinement (FY10) | 0 | 0 | 32400 | 0 | 50000 | 0 | 50000 | 0 | 0 | 50000 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | Complete from a PRRIP budget standpoint | 0 | 0 | 0 | 0
WQ-1 | C | Water Quality Monitoring (FY09-FY11) | 0 | 0 | 40000 | 40000 | 184000 | 175043.2 | 188956.8 | 176747.3 | 280000 | 225022.39 | 150000 | 156084.25 | 152000 | 173352.9 | 0 | 60585.67 | 0 | Complete from PRRIP budget standpoint | 0 | 0 | 0 | 0
|  | Sub-Total | 817212 | 192934.38 | 1270039.48 | 707092.17 | 2377669.74 | 1295310.19 | 2331183.6 | 1647379.36 | 2462500 | 1979681.89 | 2627318.18 | 2018538.38 | 2731170 | 2793500.28 | 2037308 | 1719496.12 | 2112798 |  | 1609400 | 1598000 | 1598000 | 1598000
AMP Independent Science Review
ISAC-1 | O | ISAC Stipends & Expenses (FY09-FY19) | 80000 | 0 | 115000 | 0 | 142000 | 138306.72 | 150000 | 129192.27 | 185000 | 178034.77 | 185000 | 191375.02 | 221000 | 166642.44 | 200000 | 126737.32 | 200000 | Annual stipends, meeting expenses | 200000 | 200000 | 200000 | 200000
ISAC-2 | C | Meetings, Expenses, etc. (FY08) | 0 | 0 | 5000 | 0 | 0 |  | 0 | 0 | 0 | 1250.93 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | Complete from PRRIP budget standpoint | 0 | 0 | 0 | 0
ISAC-3 | C | Initial Establishment /Planning Session Expenses (FY08) | 0 | 0 | 5000 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | Complete from PRRIP budget standpoint | 0 | 0 | 0 | 0
PD-3 | O | AMP & IMRP Peer Review (FY09-FY19) | 50000 | 0 | 105000 | 0 | 50000 | 49500 | 50000 | 0 | 115000 | 59845.5 | 90000 | 43046.75 | 108000 | 8940.75 | 318500 | 0 | 233260 | Funding for peer review of up to five documents. | 200000 | 200000 | 200000 | 200000
PD-11 | O | AMP Reporting (FY09-FY19) | 0 | 0 | 10000 | 0 | 10000 | 0 | 70000 | 24340.91 | 25000 | 7192.33 | 25000 | 11399.38 | 25000 | 13162.07 | 14000 | 9137.62 | 14000 | Estimated meeting costs for AMP Reporting Session in fall 2015 | 14000 | 14000 | 14000 | 14000
PD-21 | O | PRRIP Publications (FY14-FY19) | [12 empty] | 0 | 0 | 20000 | 7347.6 | 16060 | Estimated costs for PRRIP publication in refereed journals of up to seven manuscripts. | 20000 | 20000 | 20000 | 20000
|  | Sub-Total | 130000 | 0 | 240000 | 0 | 202000 | 187806.72 | 270000 | 153533.18 | 325000 | 246323.53 | 300000 | 245821.15 | 354000 | 188745.26 | 552500 | 143222.54 | 463320 |  | 434000 | 434000 | 434000 | 434000
|  | AMP Sub-Total | 1172212 | 219829.08 | 3285039.48 | 1903536.54 | 4369669.74 | 1913374.83 | 5191974.81 | 3128430.7 | 4435500 | 3465520.73 | 4897551.18 | 3872945.24 | 5068239 | 4302955.07 | 3546888 | 2464721.95 | 3844608 | 36495322.14 | 2988400 | 2827000 | 2957000 | 2607000
|  |  | Column A | Column A | Column C | Column B | Column E | Column C | Column G | Column D | Column I | Column E | Column F | Column F | Column H | Column G | Column J | Column H | Column I | Estimated First Increment Total ($187M available in 2005 dollars) | Column K | Column L | Column M | Column N
PRRIP BUDGET TOTALS |  |  | 2434261 | 1058592.22 | 11053964 | 3559179.93 | 16326458.24 | 13587723.45 | 17734817.71 | 10245625.14 | 19430000 | 9430963.7 | 25173351.18 | 15877903.97 | 27050139 | 23347350.36 | 25261911 | 5081882.19 | 26492267.54 | 186783708.57 | 26395556.29 | 26832550.26 | 12423267.7 | 12450845.82
Status Label |  | * All budget numbers in 2005 dollars
O = Ongoing, N = New, C = Complete
AMP Project ID Labels:
G = Geomorphology
H = Hydrology
IMRP = Integrated Monitoring and Research Plan
PD = General Activities/Program Development
PS = Pallid Sturgeon
TP = Terns/Plovers
WC = Whooping Cranes
WMV = Wet Meadows/Vegetation
WQ = Water Quality